## Gate Sign-off
Phase | Module | Gate status | Signed off by | Date | Notes
Phase 0 | Staging + UI shell | ✅ Pass |  | 2026-05-19
Phase 1 | Auth, settings, Super Admin | ✅ Pass |  | 2026-06-04 | Local UAT
Phase 2 | Customers | ✅ Pass |  | 2026-06-04 | Local UAT
Phase 3 | Suppliers | ✅ Pass |  | 2026-06-04 | Local UAT
Phase 4 | Ledger + banks/cash | ⏳ Pending |  |  | Fill after L1–G2
Phase 5 | Invoices + payments | ⏳ Pending |  |  | Fill after INV1–G2
Phase 6 | Repair jobs + tasks | ⏳ Pending |  |  | Fill after R1–G2
Phase 7 | Parts stock | ⏳ Pending |  |  | Fill after P1–G2
— | Bodywork jobs | ⏳ Pending |  |  | Fill after BW1–G2

## UAT Test Cases
Phase | Test ID | Category | Test Case | Preconditions | Steps | Expected Result | Test Account | Environment | Priority | Pass/Fail | Tester | Date Tested | Notes
Phase 0 | P0-01 | Deploy & shell | Staging loads over HTTPS | Staging URL available | 1. Open staging URL in browser | Page loads over HTTPS with no certificate errors | N/A | Staging | High
Phase 0 | P0-02 | Auth | Owner can log in | Seed applied; owner account exists | 1. Open login page 2. Enter owner@demo.garage / demo 3. Sign in | Dashboard loads; sidebar and top bar visible | owner@demo.garage / demo | Local or Staging | High
Phase 0 | P0-03 | UI shell | Dashboard shell visible | Logged in as owner | 1. After login review main layout | Sidebar nav + top bar + KPI placeholders visible | owner@demo.garage / demo | Local or Staging | High
Phase 0 | P0-04 | UI shell | Sidebar collapse | Logged in | 1. Click menu (☰) to collapse 2. Expand again | Sidebar collapses to icons; expands back | owner@demo.garage / demo | Local or Staging | Medium
Phase 0 | P0-05 | UI shell | Light and dark mode | Logged in | 1. Toggle light/dark theme | All text readable (nav tables KPIs) | owner@demo.garage / demo | Local or Staging | Medium
Phase 0 | P0-06 | Auth | Logout and login again | Logged in | 1. Sign out 2. Sign in again | Returns to login; re-login works | owner@demo.garage / demo | Local or Staging | High
Phase 0 | P0-07 | Quality | No console errors on login | Browser devtools open | 1. Open login 2. Sign in 3. Check console (F12) | No red errors on login flow | owner@demo.garage / demo | Local or Staging | Medium
Phase 1 | A1 | Deploy & health | API health endpoint | API running | 1. Open http://localhost:4000/health or staging API /health | JSON: ok true and phase 1 | N/A | Local or Staging | High
Phase 1 | A2 | Deploy & health | Web login page loads | Web running | 1. Open http://localhost:3011/login or staging web login | Login page loads; no console errors | N/A | Local or Staging | High
Phase 1 | A3 | Deploy & health | Staging build banner (staging only) | Web deployed on Railway; NEXT_PUBLIC_APP_ENV=staging; build sets NEXT_PUBLIC_BUILD_SHA | 1. Use Railway web service public URL (not API) 2. Log in 3. Top amber bar shows STAGING and build abc1234 | Amber bar: STAGING — test data only · deploy v2 · build {7-char SHA}. Skip if staging URL 404 — get URL from Railway → web → Networking | N/A | Staging only | Medium |  |  | FAIL if using mygarageweb-production URL — returns 404 (verify domain in Railway)
Phase 1 | A4 | Deploy & health | API proxy via web | Web + API running | 1. Open /api/backend/health on web origin | Same health JSON as direct API | N/A | Local or Staging | Low
Phase 1 | B1 | Super Admin | Super Admin login and nav | admin@demo.garage seeded | 1. Log in as admin@demo.garage / demo | Super Admin appears in nav; platform access | admin@demo.garage / demo | Local or Staging | High
Phase 1 | B2 | Super Admin | Garage list and searchable table | Logged in as Super Admin | 1. Open Super Admin 2. Verify Demo Garage listed | Searchable table shows garages; Demo Garage present | admin@demo.garage / demo | Local or Staging | High
Phase 1 | B3 | Super Admin | Create garage (full registration) | Super Admin access | 1. Add garage: name slug director address contact phone VAT (opt) owner email temp password 2. Save | Garage created; new row in list | admin@demo.garage / demo | Local or Staging | High
Phase 1 | B4 | Super Admin | New owner forced password change | Garage created in B3 | 1. Log in as new owner with temp password | Redirected to change password; then normal access | New owner email | Local or Staging | High
Phase 1 | B5 | Super Admin | Module toggles draft + Save + confirm | Super Admin; garage in list | 1. Edit garage modules 2. Toggle several 3. Click Save 4. Confirm in dialog 5. Refresh | Changes saved only after Save+confirm; persist after refresh | admin@demo.garage / demo | Local or Staging | High
Phase 1 | B6 | Super Admin | Module changes not instant-save | Super Admin editing modules | 1. Toggle one module only (do not Save) | UI shows unsaved state; API/list unchanged until Save | admin@demo.garage / demo | Local or Staging | Medium
Phase 1 | B7 | Super Admin | Discard module edits | Super Admin editing modules | 1. Toggle modules 2. Close/cancel without saving | Changes discarded; refresh shows original modules | admin@demo.garage / demo | Local or Staging | Medium
Phase 1 | B8 | Super Admin | Suspend and activate garage | Super Admin; test garage exists | 1. Suspend garage 2. Try owner login 3. Activate garage 4. Login again | Suspended: owner cannot use app; active: works | admin@demo.garage / demo | Local or Staging | High
Phase 1 | B9 | Super Admin | Audit log platform actions | Actions performed in B2-B8 | 1. Open Super Admin audit log | Recent garage/module actions visible | admin@demo.garage / demo | Local or Staging | Medium
Phase 1 | C1 | Settings | Owner login | Seed applied | 1. Log out 2. Log in owner@demo.garage / demo | Owner dashboard loads | owner@demo.garage / demo | Local or Staging | High
Phase 1 | C2 | Settings | Add expense category | Logged in as owner | 1. Settings 2. Add expense category | Category appears in list | owner@demo.garage / demo | Local or Staging | High
Phase 1 | C3 | Settings | VAT rates visible | Logged in as owner | 1. Open Settings VAT section | Seeded VAT rates listed | owner@demo.garage / demo | Local or Staging | Medium
Phase 1 | D1 | Roles | Default roles listed | Logged in as owner | 1. Settings → Manage roles | Manager Mechanic Staff (defaults) visible | owner@demo.garage / demo | Local or Staging | High
Phase 1 | D2 | Roles | Searchable roles table | Logged in as owner | 1. Manage roles 2. Use search | Table filters correctly | owner@demo.garage / demo | Local or Staging | Medium
Phase 1 | D3 | Roles | Edit Mechanic permissions | Logged in as owner | 1. Edit access on Mechanic 2. Enable Customers View only 3. Save | Permissions saved | owner@demo.garage / demo | Local or Staging | High
Phase 1 | D4 | Roles | Add custom role | Logged in as owner | 1. Add role e.g. Workshop lead with limited access | Role appears in list | owner@demo.garage / demo | Local or Staging | Medium
Phase 1 | E1 | Team | Team list searchable | Logged in as owner | 1. Open Team | Owner manager mechanic visible; search works | owner@demo.garage / demo | Local or Staging | High
Phase 1 | E2 | Team | Add staff user | Logged in as owner; customers.write | 1. Team → Add user with email name role password | User appears in table | owner@demo.garage / demo | Local or Staging | High
Phase 1 | E3 | Team | Edit display name | Logged in as owner | 1. Edit mechanic 2. Change display name 3. Save | List updates | owner@demo.garage / demo | Local or Staging | Medium
Phase 1 | E4 | Team | Change user role | Logged in as owner | 1. Edit mechanic 2. Change role to Manager 3. Save | Role updated in list | owner@demo.garage / demo | Local or Staging | High
Phase 1 | E5 | Team | Role change affects nav after re-login | Role changed in E4 | 1. Sign out 2. Log in as that user | Sidebar/permissions match new role | mechanic or test user | Local or Staging | High
Phase 1 | E6 | Team | Disabled user cannot log in (explicit message) | Test user disabled in Team | 1. Disable test user 2. Attempt login with correct password | Message: account deactivated contact garage administrator (not invalid email/password) | Disabled test user | Local or Staging | High
Phase 1 | E7 | Team | Owner edit restrictions | Logged in as owner | 1. Edit owner account | Cannot disable owner or improperly change owner role | owner@demo.garage / demo | Local or Staging | Medium
Phase 1 | F1 | Permissions | Mechanic restricted nav | After D3 (customers view only) | 1. Log in as mechanic | Customers visible if granted; Ledger/Partners hidden or access denied | mechanic@demo.garage / demo | Local or Staging | High
Phase 1 | F2 | Permissions | Manager default access | Logged in as manager | 1. Log in manager@demo.garage / demo | Broad access per Manager defaults (customers suppliers settings etc.) | manager@demo.garage / demo | Local or Staging | High
Phase 1 | F3 | Permissions | Mechanic cannot manage roles | Logged in as mechanic | 1. Try Settings → Manage roles | Blocked or nav hidden | mechanic@demo.garage / demo | Local or Staging | Medium
Phase 1 | F4 | Permissions | Module disabled hides nav | Super Admin disabled module for demo garage | 1. As owner refresh app | Disabled module not in sidebar | owner@demo.garage / demo | Local or Staging | Medium
Phase 1 | G1 | Sign-off | Audit log tenant actions | Settings/team/role changes made | 1. Super Admin audit log | Shows settings users role changes | admin@demo.garage / demo | Local or Staging | Medium
Phase 1 | G2 | Sign-off | Phase 1 gate pass | All Phase 1 tests reviewed | 1. Complete checklist 2. Record sign-off | No blocking bugs; gate Pass documented | Various | Local or Staging | High
Phase 2 | H1 | Customers | Customers nav and module | Customers module enabled; owner login | 1. Open Customers | List page loads with searchable table | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H2 | Customers | Add individual + vehicle (modal) | customers.write | 1. Add customer 2. Individual + name phone 3. Optional vehicle reg make model 4. Save | Customer in table; vehicle on detail page | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H3 | Customers | Add business account customer | customers.write | 1. Add customer 2. Business + account terms credit limit billing 3. Save | Account customer saved; badge in table | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H4 | Customers | Search by name (table search) | Customers exist | 1. Use table search for partial name | Matching rows shown | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H5 | Customers | Search by registration | Customer with vehicle exists | 1. Search vehicle registration | Customer found | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H6 | Customers | Edit customer (modal) | customers.write | 1. Edit customer 2. Change phone/name 3. Save | Updates persist after refresh | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H7 | Customers | View detail and add vehicle | Customer exists | 1. Click View 2. Add second registration on detail page | Both vehicles listed | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H8 | Customers | Archive customer (confirm) | customers.write | 1. Archive customer 2. Confirm | Removed from active list | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H9 | Customers | Show archived + restore | Archived customer exists | 1. Enable Show archived 2. Restore customer 3. Confirm | Customer back in active list | owner@demo.garage / demo | Local or Staging | High
Phase 2 | H10 | Customers | Mechanic read-only | Mechanic has customers.read only | 1. Log in as mechanic 2. Open Customers | Can view; no add/edit/archive (or buttons hidden) | mechanic@demo.garage / demo | Local or Staging | High
Phase 2 | H11 | Customers | Permission denied without customers.read | Mechanic role lacks customers.read | 1. Log in as mechanic | Customers hidden or access denied | mechanic@demo.garage / demo | Local or Staging | Medium
Phase 2 | H12 | Customers | Legacy /customers/new redirect | Web deployed | 1. Open /customers/new | Redirects to /customers (modal add) | N/A | Local or Staging | Low
Phase 2 | G2 | Sign-off | Phase 2 gate pass | Phase 2 tests complete | 1. Record sign-off in PROGRESS.md | Phase 2 Pass | Various | Local or Staging | High
Phase 3 | S1 | Suppliers | Suppliers nav and module | Suppliers module enabled; owner login | 1. Open Suppliers | Searchable table loads; seeded suppliers may show | owner@demo.garage / demo | Local or Staging | High
Phase 3 | S2 | Suppliers | Add supplier (modal) | suppliers.write | 1. Add supplier 2. Fill name contact VAT address 3. Save | Supplier appears in table | owner@demo.garage / demo | Local or Staging | High
Phase 3 | S3 | Suppliers | Search supplier | Suppliers exist | 1. Use table search name/email/phone/VAT | Matching rows shown | owner@demo.garage / demo | Local or Staging | High
Phase 3 | S4 | Suppliers | Edit supplier (modal) | suppliers.write | 1. Edit supplier 2. Change phone 3. Save | Updates persist | owner@demo.garage / demo | Local or Staging | High
Phase 3 | S5 | Suppliers | Deactivate supplier (confirm) | suppliers.write | 1. Deactivate 2. Confirm | Status inactive; hidden from default list | owner@demo.garage / demo | Local or Staging | High
Phase 3 | S6 | Suppliers | Show inactive + activate | Inactive supplier exists | 1. Show inactive 2. Activate 3. Confirm | Supplier active again | owner@demo.garage / demo | Local or Staging | High
Phase 3 | S7 | Suppliers | Seeded demo suppliers | pnpm db:seed run | 1. Open Suppliers as owner | Euro Car Parts and GSF Car Parts listed (if seeded) | owner@demo.garage / demo | Local | Medium
Phase 3 | S8 | Suppliers | Mechanic without suppliers.write | Mechanic lacks suppliers.write | 1. Log in as mechanic | View only or no edit/deactivate buttons | mechanic@demo.garage / demo | Local or Staging | Medium
Phase 3 | G2 | Sign-off | Phase 3 gate pass | Phase 3 tests complete | 1. Record sign-off | Phase 3 Pass | Various | Local or Staging | High
Phase 4 | L1 | Ledger | Ledger nav and page load | Ledger module enabled; owner login | 1. Open Ledger from sidebar | Accounts and Entries tabs visible; no errors | owner@demo.garage / demo | Local or Staging | High
Phase 4 | L2 | Ledger | Add bank account | ledger.write; owner login | 1. Ledger → Accounts tab 2. Add account 3. Type Bank 4. Name + opening balance 5. Save | Bank account appears in list with correct balance | owner@demo.garage / demo | Local or Staging | High
Phase 4 | L3 | Ledger | Add cash account | ledger.write | 1. Add account 2. Type Cash 3. Save | Cash account listed separately from bank | owner@demo.garage / demo | Local or Staging | High
Phase 4 | L4 | Ledger | Post expense (pending) | Payment account exists; expense category seeded | 1. Entries tab 2. Add expense 3. Select account category amount 4. Save | Entry status Pending; account balance unchanged until posted | manager@demo.garage / demo | Local or Staging | High
Phase 4 | L5 | Ledger | Manager checks expense | Pending expense from L4 | 1. Log in as manager 2. Open entry 3. Check / approve for review | Status moves to Checked (awaiting owner post) | manager@demo.garage / demo | Local or Staging | High
Phase 4 | L6 | Ledger | Owner posts expense | Checked expense from L5 | 1. Log in as owner 2. Approve/post entry | Status Posted; account balance decreases by amount | owner@demo.garage / demo | Local or Staging | High
Phase 4 | L7 | Ledger | Post income to bank | Bank account exists | 1. Add income entry 2. Manager check 3. Owner post | Posted income increases account balance | owner@demo.garage / demo | Local or Staging | High
Phase 4 | L8 | Ledger | Cannot edit posted entry | Posted entry exists | 1. Open posted entry 2. Attempt edit | Edit blocked or save fails with clear message | owner@demo.garage / demo | Local or Staging | High
Phase 4 | L9 | Ledger | Void posted entry (reversal) | Posted entry exists | 1. Void entry with reason 2. Confirm | Entry voided; balance reversed; audit logged | owner@demo.garage / demo | Local or Staging | Medium
Phase 4 | L10 | Ledger | Manager cannot post entries | Checked entry exists | 1. Log in as manager 2. Try to post/approve to ledger | Forbidden — only owner can post | manager@demo.garage / demo | Local or Staging | Medium
Phase 4 | L11 | Ledger | Mechanic read-only ledger | Mechanic lacks ledger.write | 1. Log in as mechanic 2. Open Ledger if visible | View only or nav hidden per role | mechanic@demo.garage / demo | Local or Staging | Medium
Phase 4 | G2 | Sign-off | Phase 4 gate pass | Phase 4 tests complete | 1. Record Pass in PROGRESS.md gate table | Phase 4 signed off | Various | Local or Staging | High
Phase 5 | INV1 | Invoices | Invoices nav and list | Invoices module enabled; owner login | 1. Open Invoices | Searchable invoice table loads; seeded ABC invoices may show | owner@demo.garage / demo | Local or Staging | High
Phase 5 | INV2 | Invoices | Create invoice with lines + VAT | Customer exists; invoices.write | 1. Create invoice 2. Add customer + lines 3. Toggle VAT on/off 4. Save | Invoice created with correct net/VAT/total | owner@demo.garage / demo | Local or Staging | High
Phase 5 | INV3 | Invoices | Download invoice PDF | Invoice exists | 1. Open invoice 2. Download PDF | PDF downloads; shows garage + customer + line items | owner@demo.garage / demo | Local or Staging | High
Phase 5 | INV4 | Invoices | Send invoice (mark sent) | Draft invoice exists | 1. Send invoice action | Status updates to Sent (or equivalent) | owner@demo.garage / demo | Local or Staging | Medium
Phase 5 | INV5 | Invoices | Record payment across multiple invoices | Several open invoices for same customer | 1. Record payment e.g. £700 2. Allocate across 4 invoices (mix paid + part-paid) | Payment saved; allocations shown per invoice | owner@demo.garage / demo | Local or Staging | High
Phase 5 | INV6 | Invoices | Customer balance after payment | Payment recorded in INV5 | 1. Open customer detail or invoice list 2. Review balance/outstanding | Customer balance matches invoices minus allocations | owner@demo.garage / demo | Local or Staging | High
Phase 5 | INV7 | Invoices | Undo payment allocation (owner) | Allocation exists from INV5 | 1. As owner remove one allocation 2. Confirm | Allocation removed; invoice statuses recompute | owner@demo.garage / demo | Local or Staging | High
Phase 5 | INV8 | Invoices | Invoice status badges | Mix of paid part-paid unpaid invoices | 1. Review invoice list statuses | Paid / Part paid / Unpaid badges correct | owner@demo.garage / demo | Local or Staging | Medium
Phase 5 | INV9 | Invoices | Deposit line on invoice | Job or manual invoice with deposit | 1. Create or view invoice with deposit 2. Verify totals | Deposit shown; balance due correct | owner@demo.garage / demo | Local or Staging | Medium
Phase 5 | G2 | Sign-off | Phase 5 gate pass | Phase 5 tests complete | 1. Record Pass in PROGRESS.md | Phase 5 signed off | Various | Local or Staging | High
Phase 6 | R1 | Repair | Repair nav and job list | Repair module enabled | 1. Open Repair | Job list loads; seeded demo jobs visible | owner@demo.garage / demo | Local or Staging | High
Phase 6 | R2 | Repair | Create repair job | repair.write; customer with vehicle | 1. New job 2. Customer + vehicle + description 3. Save | Job appears in list with job number | owner@demo.garage / demo | Local or Staging | High
Phase 6 | R3 | Repair | Add tasks and assign mechanic | Open repair job | 1. Add task(s) 2. Assign mechanic 3. Save | Tasks listed with assignee | manager@demo.garage / demo | Local or Staging | High
Phase 6 | R4 | Repair | Job status workflow | Job in quote state | 1. Send quote 2. Customer approve 3. Move to In progress | Status transitions follow workflow; buttons match state | manager@demo.garage / demo | Local or Staging | High
Phase 6 | R5 | Repair | Mechanic workshop tabs | Mechanic has repair View (read+work) | 1. Log in as mechanic 2. Open Repair | All / My tasks / Available to claim tabs visible | mechanic@demo.garage / demo | Local or Staging | High
Phase 6 | R6 | Repair | Claim unassigned task | Job with unassigned task exists | 1. As mechanic open Available to claim 2. Claim task | Task assigned to mechanic; moves to My tasks | mechanic@demo.garage / demo | Local or Staging | High
Phase 6 | R7 | Repair | Complete task and QC flow | Task in progress | 1. Mark task complete 2. Job moves to Testing/QC 3. Manager sign-off or send back | QC flow works; job can reach Ready | mechanic@demo.garage / demo | Local or Staging | High
Phase 6 | R8 | Repair | All tasks visible on job detail (workshop view) | Mechanic on job with others' tasks | 1. Open job detail as mechanic | All tasks visible; actions only on own/claimable tasks | mechanic@demo.garage / demo | Local or Staging | High
Phase 6 | R9 | Repair | Generate invoice from job | Job ready with tasks/parts | 1. Generate invoice from job 2. Review lines | Invoice created with labour/parts lines linked to job | manager@demo.garage / demo | Local or Staging | High
Phase 6 | R10 | Repair | Ledger income from job invoice | Invoice posted/paid from job | 1. Check Ledger entries | Repair income entries exist for job | owner@demo.garage / demo | Local or Staging | Medium
Phase 6 | G2 | Sign-off | Phase 6 gate pass | Phase 6 tests complete | 1. Record Pass in PROGRESS.md | Phase 6 signed off | Various | Local or Staging | High
Phase 7 | P1 | Parts | Parts nav and catalog | Parts module enabled | 1. Open Parts | Searchable parts table; seeded parts may show | owner@demo.garage / demo | Local or Staging | High
Phase 7 | P2 | Parts | Add part with qty and min level | parts.write | 1. Add part 2. Set quantity on hand + min quantity 3. Save | Part in catalog with stock levels | owner@demo.garage / demo | Local or Staging | High
Phase 7 | P3 | Parts | Vehicle-specific fitments | parts.write | 1. Add/edit part 2. Set fitment type Vehicle-specific 3. Add make/model/year 4. Save | Fitments saved and shown on part | owner@demo.garage / demo | Local or Staging | Medium
Phase 7 | P4 | Parts | Receive stock | Part exists | 1. Receive stock action 2. Enter qty 3. Confirm | Quantity on hand increases | owner@demo.garage / demo | Local or Staging | High
Phase 7 | P5 | Parts | Stock picker on repair job (vehicle match) | Open repair job with vehicle; matching parts in stock | 1. Open job 2. Add stock part 3. Select from picker | Only compatible parts shown (or universal) | mechanic@demo.garage / demo | Local or Staging | High
Phase 7 | P6 | Parts | Consume part — stock decrements | Part added to job in P5 | 1. Confirm usage on job 2. Check Parts catalog qty | Stock quantity decreased by amount used | owner@demo.garage / demo | Local or Staging | High
Phase 7 | P7 | Parts | Part line on job invoice | Job with parts usage | 1. Generate invoice from job | Parts lines appear on invoice with correct amounts | manager@demo.garage / demo | Local or Staging | High
Phase 7 | P8 | Parts | Return unused part to stock | Part usage on open job | 1. Return part from job 2. Confirm | Stock restored; usage removed from job | mechanic@demo.garage / demo | Local or Staging | High
Phase 7 | P9 | Parts | Low-stock indicator | Part qty at or below min level | 1. Open Parts list 2. Find low-stock part | Low-stock badge or highlight visible | owner@demo.garage / demo | Local or Staging | Medium
Phase 7 | G2 | Sign-off | Phase 7 gate pass | Phase 7 tests complete | 1. Record Pass in PROGRESS.md | Phase 7 signed off | Various | Local or Staging | High
Bodywork | BW1 | Bodywork | Bodywork nav and job list | Bodywork module enabled | 1. Open Bodywork (/bodywork) | Job list loads; seeded BWJ jobs may show | owner@demo.garage / demo | Local or Staging | High
Bodywork | BW2 | Bodywork | Create bodywork job | bodywork.write; customer exists | 1. New job 2. Customer vehicle panel colour 3. Insurance source if applicable 4. Save | Job created with bodywork fields | manager@demo.garage / demo | Local or Staging | High
Bodywork | BW3 | Bodywork | Add tasks with panel | Open bodywork job | 1. Add tasks 2. Optional panel per task 3. Save | Tasks listed with panel info | manager@demo.garage / demo | Local or Staging | High
Bodywork | BW4 | Bodywork | Approve job and assign staff | Job in quote state | 1. Send/approve quote 2. Assign tasks to staff | Job approved; assignees set | manager@demo.garage / demo | Local or Staging | High
Bodywork | BW5 | Bodywork | Workshop staff tabs (bodywork View role) | User with bodywork read+work only | 1. Log in as workshop staff 2. Open Bodywork | All / My tasks / Available to claim tabs visible | bodywork@demo.garage or mechanic@demo.garage | Local or Staging | High
Bodywork | BW6 | Bodywork | Claim and complete task | Unassigned bodywork task | 1. Claim task 2. Mark in progress 3. Mark complete | No 403; task status updates | Workshop staff account | Local or Staging | High
Bodywork | BW7 | Bodywork | All tasks visible on job detail | Job with multiple assignees | 1. Open job as workshop staff | All tasks visible; Assignee column; actions on own/claimable only | Workshop staff account | Local or Staging | High
Bodywork | BW8 | Bodywork | Paint/material and outsourced costs on invoice | Job with extra costs set | 1. Set paint material outsourced amounts 2. Generate invoice | Extra lines on invoice; totals correct | manager@demo.garage / demo | Local or Staging | High
Bodywork | BW9 | Bodywork | QC flow sign-off or send back | All tasks complete | 1. Job → Awaiting QC 2. Manager QC sign-off OR send back | Sign-off → Ready; send back → tasks reopen | manager@demo.garage / demo | Local or Staging | High
Bodywork | G2 | Sign-off | Bodywork gate pass | Bodywork tests complete | 1. Record Pass in PROGRESS.md | Bodywork signed off | Various | Local or Staging | High
Reference | ACC-05 | Accounts | Workshop staff (bodywork View) | Create role: Bodywork module View only; assign team user | Use for BW5–BW7 if not using mechanic | bodywork View grants read+work at login | bodywork@demo.garage / demo | Local or Staging | Info
Reference | ACC-06 | Accounts | ABC Cabs demo customer | Seed data | Use for account-customer invoice/payment tests | Weekly account customer with vehicles and seeded invoices | N/A | Local | Info
Regression | I1 | Smoke | Login logout all roles | Accounts exist | 1. Login/logout super admin owner manager | All work | Various | Local or Staging | High
Regression | I2 | Smoke | Sidebar and dark mode | Logged in | 1. Collapse sidebar 2. Toggle theme | Works on customers and suppliers pages | owner@demo.garage / demo | Local or Staging | Medium
Regression | I3 | Smoke | No console errors main flows | DevTools open | 1. Login 2. Customers 3. Suppliers | No blocking console errors | owner@demo.garage / demo | Local or Staging | Medium
Regression | I4 | Smoke | Tenant isolation (multi-garage) | Two garages on staging | 1. Owner A login 2. Verify no Garage B data | No cross-tenant leak | Garage A owner | Staging | High
Reference | ACC-01 | Accounts | Test account reference | N/A | Super Admin: admin@demo.garage / demo | N/A | N/A | N/A | Info
Reference | ACC-02 | Accounts | Test account reference | N/A | Owner: owner@demo.garage / demo | N/A | N/A | N/A | Info
Reference | ACC-03 | Accounts | Test account reference | N/A | Manager: manager@demo.garage / demo | N/A | N/A | N/A | Info
Reference | ACC-04 | Accounts | Test account reference | N/A | Mechanic: mechanic@demo.garage / demo | N/A | N/A | N/A | Info
Reference | URL-01 | URLs | Local URLs | N/A | Web: http://localhost:3011 ¦ API: http://localhost:4000/health | N/A | N/A | Local | Info
Reference | URL-02 | URLs | Staging web URL (verify in Railway) | N/A | Get from Railway → web service → Settings → Networking → Public domain (do NOT use API domain). Old doc URL mygarageweb-production.up.railway.app returned 404 — replace with your live domain | N/A | N/A | Staging | Info